## Sheet1
Important Decision Meeting
Meeting Name | Date | Time | Location | Before Meeting | discription
Coding Language | 2016-01-28 | 4:45-5pm | library | plan for meeting and software deployment | Decided on system requirements.
REQUIREMENTS | 2016-02-01 | 11-11:25am | BO120 | Arranged a meeting with Prof. Wuthritch | Gathered requirements phase-1.
REQUIREMENTS | 2016-02-08 | 11-11:25am | BO120 | Arranged a meeting with Prof. Wuthritch | Gathered requirements phase-2.
Design | 2016-02-09 | 11-11:25am | BO120 | Basic outline of the design | The class,sequence diagram and a basic outline of the interface
SRS | 2016-02-11 | 8-8:15pm | virtual | use case,class diagram and requiremnts doc | content of SRS
First presentation | 2016-02-22 | 11-11:25am | BO120 | Done with SRS | plan for work distribution and interface design updation
Interface | 2016-03-07 | 11-11:25am | BO119 | Interface desin changes noted | What kind of changes does the interface need and funtionality
unpated interface | 2016-03-17 | 6-6:15pm | virtual | meet deadline for assigned work | final accepted interface by all team member
Project status | 2016-04-09 | 8-8:15pm | virtual | meet deadline for assigned work | database connection done and documentation status was updated with all members
Project status | 2016-04-19 | 11-11:25am | BO119 | meet deadline for assigned work | updated and final UI for report and whole project
Final 2 week a continous but informal meet took place over phone, email and face to face